## Sheet1
To ensure that Ozurdex® launches are successful, pre-launch planning involving a cross functional team is crucial to ensure an integrated approach to providing the strategic direction for launch.
Function | Allergan Owner |  | 24 months to launch | 12 months to launch | 3 months to launch | Day 0 | Post-launch | 12 months post launch
|  |  | Market Preparation | Launch plan in place | Launch phase | Launch | Evaluation | Evaluation
Include key milestone overview
Internal planning |  | Establish multi-functional internal Ozurdex® launch team. Put regular meetings in place. | Define responsibilities and accountabilities
|  |  | Provide strategic direction for access and appropriate use of Ozurdex to fulfil the potential of the brand | Share vision for Ozurdex® launch
|  |  | Guide the development of the cross functional launch project plan and the country launch plan | Review and update launch plan | Implement launch plan | Implement launch plan
Identify data gaps and regional evidence needs
|  |  | Define key performance targets and how they will be measured | Evaluate and review key performance measures |  |  | Evaluate key performance measures | Evaluate and review key performance measures
Consider life cycle management
Prepare launch timeline with key milestones
Identify people responsible for each function / milestone
|  |  | Identify resource and investment needs [sales force, promotional and training spends, etc] | Prepare P & L forecast, including key assumptions
Establish and secure required field force resource
|  |  | Create internal engagement plan | Deliver programme to keep internal stakeholders informed
|  | Regulatory | Understand timelines to approvals and licence |  |  |  | Consider post launch lifecycle management, new indications or other regulatory events
|  | Manufacturing | Engage with manufacturing to establish timelines for product supply
Marketing |  |  | Complete Ozurdex SWOT | Review and refine SWOT
Prepare a market summary of value, volume, growth rates, pateint opportunity, treatment dynamics, patient flow / pathways
|  |  | Clearly define launch opportunity [include specific patient group, customer insights, number of patients / customers, belief shift, most significant barrier, financial value, timeline] | Share vision for Ozurdex® launch
|  |  | Work with launch team to set forecasts | Complete launch forecasts | Review and update forecasts |  | Track and review against forecast
|  |  | Complete customer segmentation for physician and patient | Define customer belief shifts needed to shape market for Ozurdex®
|  |  | Define brand positioning based on the product profile | Define critical success factors
|  |  | Develop launch strategy and campaign for Ozurdex® | Campaign message test
Identify supporting evidence required to support launch
Sales and Commercial |  | Sales force management | Assess and agree resource required | Put in place sales recruitment programme | Put in place sales training programme
Market research |  |  | Review IMB and other in-country research and establish knowledge gaps
Define and understand the market for Ozurdex® incluidng competitor landscape, companies, brands and their market share
Provide information on customer segmentation, based on distinct characteristics, behaviours and needs.
Establish the unmet need for clinicians and other healthcare professionals
Market access |  |  | Understand core value analysis and competitive landscape | Identify any non-clinical data gaps, burden of disease and develop plan to gather
|  |  | Work with IMB to plan pricing strategy |  | Country price approval
|  |  | Complete country-payer mapping and identify access drivers | Specify what factors / information the payer needs to accept Ozurdex®
Define activities and materials required to achieve reimbursement
Establish the unmet need for payers
|  |  | Establish the value differentiation payers will require to support Ozurdex | Develop core value drivers | Finalise Ozurdex® value story
Training for PRAMS / RAMS
Medical affairs |  | Evidence and data generation | Assess and understand available Ozurdex® data | Specify outstanding regional clinical data gaps and develop plan to gather
Identify country data gaps and plan IITs
Identify any non-clinical data gaps, burden of disease and develop plan to gather
|  | KOL advocacy | Engage with IMB to understand future study plans
Plan and deliver country advisory board programme
Publication / congress planning
|  | Internal engagement | Plan RSS training | Disseminate data to retina specialists (request basis)
Medical education |  |  | Complete country-KOL mapping
Engage with IMB to understand global KOL engagement opportunities [international congresses, symposia, stand-alone meetings]
|  |  | Stakeholder management plan development | Implement KOL management plan |  |  | Review KOL management plan and update
|  |  |  | Launch meeting planing |  | Launch meeting
Public relations |  |  | Complete country-media mapping (medical and trade media) | Work with IMB to use international press releases and send to country media | Work with IMB to use international press releases and send to country media | Consider issuing a press release about Ozurdex® launch | Complete country-media mapping (consumer media) | Agree % market share at which a media programme to drive patients in could be implemented
|  |  | Complete country-patient group mapping | Arrange to meet patient groups, establish relationships, share information on Allergan and Ozurdex® | Arrange to meet and brief patient groups on what Ozurdex® means for their members | Provide update to groups on launch plans |  | Consider working with groups on joint patient education programmes
Develop PR launch strategy and campaign for Ozurdex®
Training |  |  | Work with IMB to understand training materials and roll out